## Proposal
Town |  | Rowe
Status |  | Passed
Overhead distribution, miles |  | 30
Underground distribution, miles |  | 1.5
Poles |  | 963
PDUs |  | 212
PDUs per mile |  | 6.7302
Take rate |  | 60%
Subs |  | 127
Phase I: Engineering and Design
Data collection and route validation, per mile | 589.4 | 17682
Pole attachment heights, per pole | 0 | 0
Final strand maps, per mile | 189 | 5670
Fiber and splice design, per mile | 546 | 16380
Total, Design and Engineering |  | 39732
Phase II: Make Ready
Pole application Processing, per pole | 10 | 9630
Pole application fees, Eversource/Ngrid (est) | 57 | 54891
Pole application fees, Verizon | 15 | 14445
% of pole requiring make ready | 100% | 963
Make ready per pole, average (estimated) | 400 | 385200
Total, make ready |  | 465129
Construction
ONTs | 140 | 17780
Drops | 588.639 | 74757.153
Materials | 208.639 | 26497.153
Labor | 380 | 48260
Labor, overhead distribution per mile | 15570.61 | 467118.3
Materials | 8231.41 | 246942.3
Labor | 7339.2 | 220176
Labor, underground distribution per mile | 89387.8 | 134081.7
Conduit path | 78803.2 | 118204.8
Materials | 5885.4 | 8828.1
Labor | 4699.2 | 7048.8
MSTs | 480 | 48000
Subs per MST, base town | 2.34
Dispersion Factor (PDU per mile base town/case town) |  | 9.8601
Estimated MSTs Required |  | 100
MST Installation Cost | 200 | 20000
Materials | 280 | 28000
Splicing | 22 | 10472
Splices required per MST | 4.75
Total Splices required |  | 476
Splicing Cost | 22 | 10472
Testing, per MST | 42 | 4200
Traffic Control, per day, per 4 man crew | 1600 | 67200
Network Components | 100000 | 100000
Total, Construction |  | 789527.453
Program Management
Construction contractor procurement, construction bid price | 1.25% | 3876.96
Material Bidding and Procurement Management, of material costs | 1% | 4102.6755
Phase III: Procurement | subtotal: | 7979.6355
Phase IV: Project management, Total network cost | 6% | 47371.6472
Total, Program Management |  | 55351.2827
Total Cost |  | 1349739.7357
Est. Total Network Cost |  | 1300000
Constr. Costs Funded by MBI |  | 220000
Prof. Svcs. Costs Funded by MBI |  | 220000
Projected Town Contribution |  | 860000
Difference |  | -49739.7357
Project Timetable | Value
Delay/Contingency at Each Phase
Delay/Contingency for Each Phase | 10%
Legal
Start of Project |  | 2017-08-01
Agreement complete (business days) | 20 | 2017-08-31
Design and Engineering
Project Scoping, days | 10 | 2017-09-15
Pole Survey, days (poles/day), business days | 25 | 39
Pole Survey Complete |  | 2017-11-14
Design/Engineering, days (miles per day), business days | 1 | 32
Design and Engineering Completed |  | 2018-01-02
Make Ready
Pole Applications day, (poles per day) | 40 | 25
Total Pole Applications (200 each app) |  | 5
Pole Applications Complete |  | 2017-11-21
Estimating Complete (business days) | 30 | 2018-01-05
Make Ready Labor Complete (business days) | 120 | 2018-07-10
Construction
Construction, days (miles per day) | 0.75 | 42
50% Construction Complete |  | 2018-08-10
100% Construction Complete |  | 2018-09-12
Commission (business days) | 20 | 2018-10-12
104713.2827

## Towns
Liklihood | Include? | Town Name | Year | Est. Total Network Cost | Constr. Costs Funded by MBI | Prof. Svcs. Costs Funded by MBI | Projected Town Contribution | Make Ready Estimate included in budget | Public Roadway Footage | Measured Aerial Strand Footage | Mapped Utility Poles | U'G Conduit Footage | Utility Provider | Mapping Residential Units | Osmose Survey | 2010 Census Housing Units | 2000 Census Housing Units | 1990 Census Housing Units | 2010 Census Households | 2010 Census Seasonal recreational or occasional use housing units | 2010 % Seasonal recreational or occasional use | Debt Authorization | Debt Exclusion | Status | Notes | Green Light | EOCD Award | Pole Survey | Mileage | Likelihood
A | Y | Rowe | 1905-07-11 | 1300000 | 220000 | 220000 | 860000 | 360000 | 209427 | 154124 | 963 | 7700 | National Grid | 212 | Yes | 227 | 209 | 211 | 167 | 50 | 22.03% | Passed | Passed | (05) Contract Sent | Incubation; wish to work with us. |  |  | Osmose | 29.1902 | 100%

## Construction Costs
PDU/mile, base case | 66.36
Item | Price
Install 1/4" Strand, per lf | 0.5
Install Fiber Cable, per lf | 0.89
Install MST, ea | 200
Fiber Splicing, ea | 22
Fiber Testing, per MST, ea | 42
Subs/ MST | 2.34
Splicing, per MST | 4.75
Underground Trench and Conduit Install, grass or hard pack | 10
Underground Trench and Conduit Install, asphalt | 20
80/20 Sod to Asphalt Conduit build | 12
Drop, Hardware, Misc
Drop (500 ft) | 161.29
Wedge grip | 1.04
J Hook, P Hook | 4.2
NID | 21.49
ISP Jumper (25 FT) | 20.619
TOTAL | 208.639
MST (12 Port/ 1K/ft tail) | 342 | worst case
MST (4 Port/ 1K/ft tail) | 218 | typ.
Strand Hardware
Magic Mile (Est. 40 pole/mi | 2346.01 | All hardware; strand,clamps,grounding materials, lash, band/spacer, down guy, etc
TOTAL | 2346.01
Cable
Cable (96F) AVG 1.5/lf | 4910.4 | Avg. size cable, 50% add cable in lash
FOSC Splice Closures (3 per mile | 975 | B Closure/Trays, Gel seal
TOTAL | 5885.4
Materal Total | 8231.41 | Less MST
underground | 63360 | trench (20% asphalt, 80% grass)
| 5700 | microduct
| 1944 | vaults and pedestals
| 4699.2 | fiber splicing
| 3100 | vault and ped install
78803.2

## Variables
Holidays | Status
2017-01-01 | (00) No Discussion
2017-01-16 | (01) Introductory Discussions
2017-02-20 | (02) Meeting Scheduled
2017-04-17 | (03) Met With
2017-05-29 | (04) Continuing Discussions
2017-07-04 | (05 Verbal Agreement
2017-09-04 | (06) Contract Sent
2017-10-09 | (07) Contract Negotiations
2017-11-10 | (08) Signed Contract
2017-11-23 | (09) Design
2017-11-24 | (10) Procurement
2017-12-25 | (11) Construction
2018-01-01 | (12) ISP and Network Ops
2018-01-15 | (94) Crocker
2018-02-19 | (95) Fiber Connect/ HG&E
2018-04-16 | (96) Frontier
2018-05-28 | (97) Charter
2018-07-04 | (98) Comcast
2018-09-03 | (99) Cancelled / Other
2018-10-08
2018-12-12
2018-11-22
2018-11-23
2018-12-25
2019-01-01
2019-01-21
2019-02-18
2019-04-15
2019-05-27
2019-07-04
2019-09-02
2019-10-14
2019-11-11
2019-11-28
2019-11-29
2019-12-25